Budget Resolution and Reduction in Force Planning

2020-2021 Fiscal Year

| Responsible | Item | Start | End |
| --- | --- | --- | --- |
|  | Immediate |  |  |
| Human Resources | Update Seniority Lists |  |  |
|  | Review Timelines and Planning with Cabinet |  |  |
|  | Vacancy Report |  |  |
|  | MAY 2020 |  |  |
| Human Resources | Unions – review bumping and layoff processes: ACE, CSEA, POA, Teamsters, Conf, FA Associations – review notice of non-renewal and layoff processes: AMA, Confidential - Calendar review, process and steps, Exit protocols, Bumping response time, Identify liaisons for Informal Notice meetings with affected EEs, Reassignment rights, Recruitment process, timelines, Reclassification deadlines, Seniority List sign off. - Seniority List Update | May 14, 2020 | Jun 15, 2020 |
| HR/Bus Services/ Campuses | Vacancy list and Budgeted Positions: Review with Campus/CS | May 14, 2020 | May 30, 2020 |
| Business Services | Establish projected target for planning purposes |  | May 30, 2020 |
| Campuses/CS | Planning and Shared Governance - Initiate discussions and brainstorming ASAP. - Review options, ideas, analysis, consolidation, program review, reorgs, etc. | May 11, 2020 | ongoing |
| Chancellor | Meetings: - Senior Staff - Consultation Task Force (CTF) - Review and input: e.g., District v. Campus planning processes - Key group for set of recommendations - Senates and union leaders, and customary District senior administrators - APM and campus committees/councils may provide constituency input. - Chancellor’s Office Hour - Communicate extraordinary urgency of this timeline – All EEs - Communicate extraordinary changes that may be required – All EEs | May 27, 2020 | May 26, 2020 May 27, 2020 Ongoing |
|  | JUNE 2020 |  |  |
| Business Services/ Human Resources | Board Meeting – Closed Session - Negotiations All Administrators/Supervisor Meeting - Timeline and Steps, Planning Projections, Procedures - Q and A Board Meeting – Closed Session - Negotiations |  | Jun 2, 2020 Jun 5, 2020 Jun 8, 2020 |
| Campuses/CS | Planning and Shared governance - Review options, ideas, analysis, consolidation, program review, reorgs, etc. |  | Ongoing |
| Chancellor | Meetings: - Chancellor’s Office Hour |  | Ongoing |
|  | JULY 2020 |  |  |
| Campuses/CS | Planning Cont’d |  | Ongoing |
| Human Resources/Business Services | Board of Trustees – Closed Session - Negotiations |  | Jul 13, 2020 |
| Chancellor | Meetings: - Senior Staff - Consultation Task Force (CTF) - Chancellor’s Office Hour |  | Jul 14, 2020 Jul 15, 2020 Ongoing |
|  | AUGUST 2020 |  |  |
| Campuses/CS | Planning Cont’d |  | Ongoing |
| Human Resources/Business Services | Board of Trustees – Closed Session - Negotiations |  | Aug 3, 2020 |
| Business Services | Review August Revise – State Budget Adjust FHDA Budget projections |  | Aug 15, 2020 Aug 18, 2020 |
| Chancellor | Chancellor’s Cabinet: Review Adjusted Budget Projections Meetings: - Senior Staff - Consultation Task Force (CTF) - Chancellor’s Office Hour |  | Aug 18, 2020 Aug 25, 2020 Aug 27, 2020 Aug 26, 2020 Ongoing |
|  | SEPTEMBER 2020 |  |  |
| Campuses/CS | Planning Cont’d |  | Ongoing |
| Human Resources/Business Services | Board of Trustees – Closed Session - Negotiations |  | Sep 14, 2020 |
|  | OCTOBER 2020 |  |  |
| Campus/CS | Conclude and finalize recommendations for reductions | Oct 1, 2020 | Oct 25, 2020 |
| Human Resources/Business Services | Board of Trustees – Closed Session - Negotiations |  | Oct 5, 2020 |
| Human Resources | Finalize Seniority Lists Finalize Elimination Forms/Spreadsheet, Seniority and Bumping provisions, Contract provisions - all employee units |  | Oct 30, 2020 |
| Chancellor | Meetings: - Senior Staff - Consultation Task Force (CTF) |  | Oct 6, 2020 Oct 10, 2020 |
|  | NOVEMBER 2020 |  |  |
| Campus/CS Human Resources Chancellor Cabinet | Reduction Plan/Cut List – V.1 - Campus/CS Submission - HR bumping analysis - Cabinet review |  | Nov 1, 2020 Nov 12, 2020 Nov 13, 2020 |
| Campus/CS | Reorganization changes due date - Concurrent with Cut List - Any/All subsequent changes must be submitted to Cabinet for review and approval. |  | Nov 1, 2020 |
| Human Resources/Business Services | Board of Trustees – Closed Session - Negotiations |  | Nov 2, 2020 |
| Chancellor Cabinet Human Resources Chancellor Cabinet | Reduction Plan/Cut List – V.2 - Cabinet Adjustments Discussion and Edits - HR bumping analysis - Cabinet review and Final Edits |  | Nov 20, 2020 Dec 1, 2020 Dec 1, 2020 |
|  | DECEMBER 2020 |  |  |
| Campus/CS | Final Reduction Plan/Cut List to Chancellor’s Cabinet - Cabinet to Review |  | Dec 8, 2020 |
| Human Resources Human Resources/ Chancellor Cabinet | Final Bumping Analysis Final Cut List and Effects/Bumping Report | Dec 8, 2020 | Dec 11, 2020 Dec 15, 2020 |
| Human Resources/Business Services | Board of Trustees – Closed Session - Negotiations - Discipline/Dismissal/Release |  | Dec 14, 2020 |
| Campus/CS | Final Authorization to Eliminate Forms Due | Dec 1, 2020 | Dec 16, 2020 |
| Human Resources | Final Review of all Authorization Forms |  | Dec 17, 2020 |
|  | JANUARY 2021 |  |  |
| Human Resources | Board of Trustees Meeting – Closed Session - Discipline/Dismissal/Release – Proposed Reductions |  | Jan 11, 2021 |
|  | Admin/Supv Training - Conducting Informal Notice meetings - Establishing a supportive environment; dealing with grief |  | Jan 8, 2021 |
| Campus/CS w Human Resources | Informal Notice to Classified, Faculty, and Admin | Jan 11, 2021 | Jan 31, 2021 |
| Human Resources | Formal Notice to FA – potentially affected faculty positions |  | Jan 30, 2021 |
|  | FEBRUARY 2021 |  |  |
| Human Resources | Board of Trustees Meeting - Closed Session - Discipline/Dismissal/Release |  | Feb 1, 2021 |
| Human Resources | Workshops and Support - Job hunting, Resume writing, Interviewing skills, EAP, CalSTRS/CalPERS – Retirement options and planning, Benefits after separation, Resources – job fairs, job sites, webpages, etc. | Feb 1, 2021 | Mar 15, 2021 |
|  | FSA Report/Updates - Final adjustments to bumping, other options | Feb 15, 2021 | Feb 17, 2021 |
|  | Board Action Item Documents Due - Non-Renewal Administrators - Non-Renewal Faculty - Classified Position Elimination and Notice of Layoff |  | Feb 23, 2021 |
|  | Update Layoff Options Notice (Template) Update Layoff/Bumping Options Notice Initiate Layoff Options Review |  | Feb 28, 2021 |
|  | MARCH 2021 |  |  |
| Human Resources | Board of Trustees Meeting - Closed Session - Discipline/Dismissal/Release - Open Session - Board Action – Notice of Non-Renewal Administrators - Board Action – Notice of Non-Renewal Faculty - Board Action – Classified Position Elimination and Notice of Layoff to Affected Employees - Mail/Distribute Notice of Non-Renewal/Release |  | Mar 1 or 8, 2021 March 15, 2021 |
|  | APRIL 2021 |  |  |
| Human Resources | Formal Classified Layoff Notice to Unions Formal Classified Layoff Notice to Employees |  | Apr 12, 2021 Apr 26 2021 |
|  | MAY 2021 |  |  |
| Human Resources | Finalize Exit Protocol Adjustments - Finalize process for meetings with EEs at each location - Keys, PCs, paperwork, etc. Email, MyPortal status. Educational or other assistance beyond layoff effective date | May 1, 2021 | May 28, 2021 |
|  | JUNE 2021 |  |  |
|  | Board Closed Session - Discipline/Dismissal/Release - Negotiations |  | Jun 7, 2021 |
|  | Exit Meetings with Employees Transition Team Meetings with transitioning employees | Jun 1, 2021 | Jun 21, 2021 |
|  | Layoff or Nonrenewal/End of Contract |  | Jun 25, 2021 Jun 30, 2021 |
|  | 39 Month Reemployment List Update |  | Jun 30, 2021 |