## Slide 1: Midterm Report Review Advisory Council June 4, 2021

## Slide 2: Midterm Report Study Group Update
Process
Timeline
Next Steps
Deliverable: Midterm Report (Oct 2021 submission)
The Ask:
Provide Midterm Report Feedback HERE

## Slide 3: Midterm Report Components
Institutional Set Standards
Targets & Goals
Institutional Effectiveness
Team Recommendations
Participatory Governance
Governance Councils
Student Learning Outcomes
Course Level, Service Area
Action Plans: QFEs
Improvement Areas
Educational Pathways
Guided Pathways
Institutional Performance
Improvement
Recommendations
Quality Focus Essays
Don’t forget the Fiscal Report!

## Slide 4: Midterm Report Organization
Study Group
Steering Committee
Midterm Report
Staff
Support
Faculty, Classified Staff, Administrators
Staff support includes ALO, Instructional Services Coordinator, Marketing Supervisor, Contractor

## Slide 5: Midterm Report Process
Monthly Study Group meetings
Bi-weekly Study Group team leads meetings
Bi-weekly Steering Committee meetings
Weekly operations logistics meetings
Quarterly presentations at Advisory Council

## Slide 6: Midterm Report Timeline Review
Fall 2020
Winter 2021
Spring 2021
Summer 2021
Oct:
Study group formed (AC)
Dec:
Team Onboarding
Jan-April: Identify evidence, processes
April-May:
Writing
June:
Constituency Feedback
June-July:
Format Report
Aug:
Board Approval

## Slide 7: Timeline Review
June
July
Aug
Oct
Midterm Report Feedback
Complete Report Formatting
Submit Board Approval
Submit Midterm Report

## Slide 8: What’s next in our accreditation cycle?
Oct 2021
Jan 2022
Dec 2023
Oct 2024
June 2023
Spr 2024
ACCJC ISER Training
ISER Kickoff
Submit ISER to ACCJC
Peer Review Team Visit
Process includes formative and summative review
ISER
draft completed
Peer Review Team Feedback
10/21/21
@ 9 am

## Slide 9
Elaine Kuo Kelaiah Harris College Researcher Instructional Services Coordinator
Accreditation Liaison Officer
kuoelaine@fhda.edu harriskelaiah@fhda.edu
If you have any additional questions or comments please contact fhaccreditation@fhda.edu or visit foothill.edu/accreditation.
For more information: ACCJC Guidelines for Preparing Institutional Reports